## Sheet1
KT Plan Template
Project ID: |  | Resource Name(s): |  | Gajanan
Project Name : | Teller | Mentor Name(s) : |  | Milind Malkar
Starting Date: | 20-04-15 | Duration in person days: |  | 3
Sr. No | Activities with brief description | Training required | Time Required (in hours) | Mentor | Planned Start Date | Planned End Date | Actual start Date | Status | Actual End Date | Actual Time taken(in hours) | Comments
A | Project Induction
| OverView | Yes | 1 | Milind Malkar |  |  | 2022-12-08 | Completed | 2022-12-08 | 4
| Project Setup | Yes | 1 | Milind Malkar
C | Total no. of Hours |  | 2 | [6 empty] | 4
B | Project specific technical training - Setup
| Bank Setup | Yes | 0.5 | Milind Malkar |  |  | 2022-12-09 | Completed | 2022-12-09 | 0.5
| Branch Setup | Yes | 0.5 | Milind Malkar |  |  | 2022-12-09 | Completed | 2022-12-09 | 0.5
| User Maintenance | Yes | 2 | Milind Malkar |  |  | 2022-12-11 | Completed | 2022-12-12 | 2
| Limit Setup | Yes | 1 | Milind Malkar
| Transaction Code | Yes | 1 | Milind Malkar
| Forex Fee | Yes | 2 | Milind Malkar
| Tariff Maintenance | Yes | 1 | Milind Malkar |  |  | 2022-12-13 | Completed | 2022-12-13 | 1
| Charge Package | Yes | 1 | Milind Malkar |  |  | 2022-12-14 | Completed | 2022-12-14 | 1
| Total no. of Hours |  | 9 | [6 empty] | 5
B | Project specific technical training
| Account Inquiry | Yes | 0.5 | Milind Malkar |  |  | 2022-12-15 | Completed | 2022-12-15 | 0.5
| Account Statement | Yes | 0.5 | Milind Malkar
| Cash Deposit | Yes | 2 | Milind Malkar |  |  | 2022-12-16 | Completed | 2022-12-19 | 2
| Cash Withdrawal | Yes | 1 | Milind Malkar |  |  | 2022-12-20
| Cheque Deposit | Yes | 1
| Mixed Deposit | Yes | 2
| Trasfer | Yes | 1
| Forex Purchase | Yes | 1
| Forex Sell | Yes | 1
| Earmark | Yes | 1
| Earmark Bulkupload | Yes | 1
| Journal | Yes | 1
|  |  | 13 | [6 empty] | 2.5
| Grand Total |  | 24 | [6 empty] | 11.5
Prepared By Mentor |  |  |  |  | Suggestions by Mentor
Signed |  | Milind Malkar
Date:15-Apr-15
Sign off By associate |  |  |  |  | Suggestions by associate
Signed |  | Gajanan Nandavdekar
Date: 15-Apr-15
Note on B8: Serial Number
Note on C8: Enter brieff description of activity
Note on D8: Mention "Yes" if training required else mention "No"
Note on E8: Provide expected time required for the activity
Note on F8: Mention about who will provide the training
Note on G8: Date on which activity is planned to start
Note on H8: Date on which activity is planned to end
Note on I8: Date on which activity actually start
Note on J8: Update the status of activity
Note on K8: Date on which activity actually ends
Note on L8: Update actual time taken in completing the activity
Note on M8: Provide additional info if any